{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Roles","Ceremonias","Spring"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Roles","index":0,"n_rows":11,"n_cols":5,"rows_kept":11,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["Product Owner","César Echeverri"]
["Scrum Master","Dáberson Henao"]
[]
[]
["Team Member Transversal","Team Member Nómina","Team Member Rentas","Team Member *","Stake Holders"]
["Carlos Torres","Ciro Soto","Jhon Avila","Alexis Brito","Sergio López"]
["Deivis Marquez","Edixon Matos","Luis Rodriguez","Sebastián Castrillón","Carolina Vargas (Nómina)"]
["Gersain Castañeda","Jesus Perico","Maria Colorado","Sonia Carmona","Eramis Oliveros"]
["Pablo Quintana","Ricardo Muñoz",null,"Brahian ","Lauren Sepulveda"]
["Saúl Gómez",null,null,null,"Nori Pinilla"]
["QA (Lorena Vega)"]

{"sheet":"Ceremonias","index":1,"n_rows":8,"n_cols":9,"rows_kept":8,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["Ceremonia","Frecuencia","Día Propuesto","Hora Propuesta","Duración Estimada","Fecha Inicio","Fecha Fin","Asistentes Requeridos","Asistentes opciones (observadores)"]
["Daily","Diario","Diario","8:00 a.m","15 mins","2020-04-14","Indefinido","Scrum máster – Team member","Stakeholders – producto owner"]
["Revisión","Quincenal","Jueves ","7:00 a.m","2 horas","2020-04-16","Indefinido","Product owner – Scrum máster – Team member – Stakeholders"]
["Planeación","Quincenal","Jueves ","9:00 a.m","2 horas","2020-04-16","Indefinido","Product owner – Scrum máster – Team member – Stakeholders"]
["Retrospectiva","Quincenal","Viernes ","7:00 a.m","2 horas","2020-04-17","Indefinido","Scrum máster – Team member"]
["Segumiento Curso","Semanal","lunes","8:00 a.m","1 hora","2020-04-20","2020-05-25","Team Member"]
["Taller Curso","Semanal","lunes","9:00 a.m","1 hora","2020-04-20","2020-05-25","Team Member"]

{"sheet":"Spring","index":2,"n_rows":26,"n_cols":5,"rows_kept":26,"cut":false,"hidden":false,"merged":[[1,4,1,7],[2,0,5,0],[2,4,2,7],[3,4,3,7],[4,4,4,7],[5,4,5,7],[6,0,9,0],[6,4,6,7],[7,4,7,7],[8,4,8,7],[9,4,9,7],[10,0,13,0],[10,4,10,7],[11,4,11,7],[12,4,12,7],[13,4,13,7],[14,0,17,0],[14,4,14,7],[15,4,15,7],[16,4,16,7],[17,4,17,7],[18,0,21,0],[18,4,18,7],[19,4,19,7],[20,4,20,7],[21,4,21,7],[22,0,25,0],[22,4,22,7],[23,4,23,7],[24,4,24,7],[25,4,25,7]],"flags":["formulas_cached_only"]}
[]
["Sprint","Inicia","Termina","Requeridos","Objetivo"]
[1,"2020-04-16","2020-04-30","Team Member Transversal","Terminar de estudiar y montar las herramientas definidas para el proyecto"]
["Sprint 1","2020-04-16","2020-04-30","Team Member Nomina","Definir el product backlog – Auto estudio java (2 horas diarias del tiempo laboral 1 horas tiempo personal)\n*Requerimos el día del inicio del sprint al líder de producto para revisión y planeacion (7:00 – 11:00 a.m)\n"]
["Sprint 1","2020-04-16","2020-04-30","Team Member *","Auto estudio java (2 horas diarias del tiempo laboral 2 horas tiempo personal) "]
["Sprint 1","2020-04-16","2020-04-30","Team Member Rentas","Definir el product backlog – Auto estudio servicios spring boot"]
[2,"2020-05-04","2020-05-14","Team Member Transversal","Apoyar la ejecución de tareas de todos los integrantes. Desarrollo de HU"]
["Sprint 2","2020-05-04","2020-05-14","Team Member Nomina","Auto estudio java (2 horas diarias del tiempo laboral 2 horas tiempo personal)\n*Requerimos el día del inicio del sprint al líder de producto para revisión y planeacion (7:00 – 11:00 a.m)"]
["Sprint 2","2020-05-04","2020-05-14","Team Member *","Auto estudio java (2 horas diarias del tiempo laboral 2 horas tiempo personal) "]
["Sprint 2","2020-05-04","2020-05-14","Team Member Rentas","Inicio desarrollo Hu"]
[3,"2020-05-15","2020-05-28","Team Member Transversal","Apoyar la ejecución de tareas de todos los integrantes. Desarrollo de HU"]
["Sprint3","2020-05-15","2020-05-28","Team Member Nomina","Inicio desarrollo Hu"]
["Sprint3","2020-05-15","2020-05-28","Team Member *","Auto estudio java (2 horas diarias del tiempo laboral 2 horas tiempo personal) "]
["Sprint3","2020-05-15","2020-05-28","Team Member Rentas","Desarrollo HU"]
[4,"2020-05-29","2020-06-11","Team Member Transversal","Apoyar la ejecución de tareas de todos los integrantes. Desarrollo de HU"]
["Sprint4","2020-05-29","2020-06-11","Team Member Nomina","Desarrollo HU"]
["Sprint4","2020-05-29","2020-06-11","Team Member *","Desarrollo HU"]
["Sprint4","2020-05-29","2020-06-11","Team Member Rentas","Desarrollo HU"]
[5,"2020-06-12","2020-06-25","Team Member Transversal","Apoyar la ejecución de tareas de todos los integrantes. Desarrollo de HU"]
["Sprint5","2020-06-12","2020-06-25","Team Member Nomina","Desarrollo HU"]
["Sprint5","2020-06-12","2020-06-25","Team Member *","Desarrollo HU"]
["Sprint5","2020-06-12","2020-06-25","Team Member Rentas","Desarrollo HU"]
[6,"2020-06-26","2020-07-09","Team Member Transversal","Apoyar la ejecución de tareas de todos los integrantes. Desarrollo de HU"]
["Sprint6","2020-06-26","2020-07-09","Team Member Nomina","Desarrollo HU"]
["Sprint6","2020-06-26","2020-07-09","Team Member *","Desarrollo HU"]
["Sprint6","2020-06-26","2020-07-09","Team Member Rentas","Desarrollo HU"]